## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE | Estimation
In Progress | Luke | Warehouse employee | be able to check for and flag damaged rentals on all status changes, not just returns. | 2020-04-06 | 2020-04-08 | 1 day
In Progress | Luke/Carson/Tristen | Librarian | Add ability to blacklist customers for not returning items | 2020-04-06 | 2020-04-08 | 1 day
In Progress | Luke/Carson/Tristen | Librarian | Add view for blacklisting customers | 2020-04-06 | 2020-04-08 | 1 day
In Progress | Luke/Carson/Tristen | Librarian | Add DB column for flagging customer as blacklisted | 2020-04-06 | 2020-04-08 | 1 day
In Progress | Luke/Carson/Tristen | Librarian | Add ability to update librarians choice | 2020-04-06 | 2020-04-08 | 1 day
In Progress | Luke/Carson/Tristen | Librarian | Add DB table for librarians choice | 2020-04-06 | 2020-04-08 | 1 day