## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE:
Complete | Luke | Member | Register account | 2020-01-27 | 2020-01-29
In progress | Carson | Member | Browse items | 2020-01-26 | 2020-01-29
In progress | Tristen | Warehouse employee | Update rental status | 2020-01-28 | 2020-01-29
Complete | Luke/Carson/Tristen | Manager | Add/Remove employees | 2020-01-25 | 2020-01-29
Complete | Luke/Carson/Tristen | Member | Borrow items | 2020-01-25 | 2020-01-29