## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE | Estimation
In Progress | Carson | Manager | Turn records of items tracked by employees into a table on the desktop app | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Tristen | Member | Implement functionality to remove addresses | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Tristen | Member | Implement DB call to remove addresses (flag as not in use, but keep in DB for record purpose) | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Luke | Warehouse employee | Add ability to flag for damaged returns | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Luke | Warehouse employee | Add functionality to DB for flagging rentals | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Luke/Tristen/Carson | Librarian | Implement view for librarians | 2020-03-10 | 2020-03-11 | 2 days
In Progress | Luke/Tristen/Carson | Librarian | Implement view for viewing users history/information | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Luke/Tristen/Carson | Librarian | Implement ability to filter members by who is overdue | 2020-03-10 | 2020-03-11 | 1 day
In Progress | Luke/Tristen/Carson | Librarian | Implement librarian table in the DB for logging in | 2020-03-10 | 2020-03-11 | 1 day