## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE
In progress | Luke/Carson/Tristen | N/A | TESTING | 2020-02-10 | 2020-02-12
Complete | Luke/Carson/Tristen | N/A | DB redesign | 2020-01-30 | 2020-02-12
In progress | Luke | Warehouse employee | Update rental status of member order | 2020-02-05 | 2020-02-12
In progress | Tristen | Member | View rental history | 2020-02-05 | 2020-02-12
In progress | Carson | Warehouse employee | View detailed list of orders that are outgoing | 2020-02-05 | 2020-02-12
In Progress | Carson | Manager | Track when things are received and shipped | 2020-02-08 | 2020-02-12