## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE
In progress | Luke/Carson/Tristen | N/A | TESTING | 2020-02-10 | 2020-02-12
Complete | Luke/Carson/Tristen | N/A | DB redesign | 2020-01-30 | 2020-02-12
Complete | Luke | Warehouse employee | Implement SQL queries for gathering orders of members | 2020-02-05 | 2020-02-12
Complete | Luke | Warehouse employee | Implement filter for filtering member orders when updating rental status | 2020-02-05 | 2020-02-12
Complete | Luke | Warehouse employee | Update rental status of member order | 2020-02-05 | 2020-02-12
Complete | Tristen | Member | Implement SQL queries for gathering all orders made by members for them to view | 2020-02-08 | 2020-02-12
Complete | Tristen | Member | Design page for customer to view their history | 2020-02-08 | 2020-02-12
Complete | Tristen | Member | View rental history | 2020-02-05 | 2020-02-12
Complete | Luke | Warehouse employee | View detailed list of orders that are outgoing/incoming | 2020-02-05 | 2020-02-12
In progress | Carson | Manager | Implement SQL queries for gathering information about a single item | 2020-02-10 | 2020-02-12
In progress | Carson | Manager | Design page for manager to view history | 2020-02-10 | 2020-02-12
In Progress | Carson | Manager | view history a single item | 2020-02-08 | 2020-02-12