## Sheet1
Progress | Assignee | User Role | Feature | ETA | DEADLINE
In Progress | Luke | Manager | Implement view where stock can be managed | 2020-02-24 | 2020-02-26
In Progress | Luke | Manager | Add ability to remove items from inventory | 2020-02-24 | 2020-02-26
In Progress | Luke | Manager | Add ability to add items to inventory | 2020-02-24 | 2020-02-26
In Progress | Tristen | Manager | Implement view where you can view records of items tracked by which employee | 2020-02-24 | 2020-02-26
In Progress | Tristen | Manager | Add ability to select employee and view their records of items tracked | 2020-02-24 | 2020-02-26
In Progress | Carson | Member | Implement view for a member to view his profile | 2020-02-24 | 2020-02-26
In Progress | Carson | Member | be able to update my profile | 2020-02-24 | 2020-02-26